## Slide 1: Team OneTen Implementation Plan: Aromy
Allen, Cassandra, Daniel, Eugene & Frank

## Slide 2: Agenda
Implementation Plan Purpose
Overview
Implementation Plan
Implementation Plan Risk & Contingencies
Notes: Dan

## Slide 3: Introduction to the Implementation Plan
Purpose
Tasks and Implementation Schedule
Notes: Dan

## Slide 4: Implementation Plan
Tasks: Prepare Site Installation and Data Conversion Training Acceptance Testing PIR Final Handover: Handover documentation and Support Performance Testing Sign Off

## Slide 5
Tasks | Resources | Beginning-End Date | Time Required
Prepare Site | Networks, Computer, & Database | 11/10 | 3 Hours
Installation | Aromy & Project Team | 11/10 - 12/10 | 1 Day
Data Conversion | Project Team | 12/10 | 4 Hours

## Slide 6
Tasks | Resources | Beginning-End | Time
User Training | Aromy & Project Team | 14/10 | 1 Day
Acceptance Testing | Aromy | 14/10 - 17/10 | 4 Days
Go Live | Project Team | 18/10 | 2 Hours
Post Implementation Review | Aromy & Project Team | 17/10 - 23/10 | 7 Days

## Slide 7
Final Handover
Tasks | Resources | Date | Time
Documentation Handover | Project team | 17/10 | 1 Day
Handover to Support | Project team | 17/10 | 1 Day
Performance Testing | Project team | 17/10 - 19/10 | 2 Days
System Sign-off | Aromy | 21/10 | Hours

## Slide 8: Risks
Security
Data and Storage
Future Protection and Risk minimisation

## Slide 9: Conclusion