## Sheet1
Formal meetings | Date | involves
Interview Product Owner | 8/8/2022 | client and team
System Overview report | 14/8/2022 | client and team
Iteration 1 report | 21/8/2022 | client
Iteration handover for acceptance testing | 28/8/2022 | client
PIR | 2/9/2022 | client and team
Iteration 2 report | 11/9 | client
Iteration handover for acceptance testing | 21/9/2022 | client
PIR | 10/10/2022 | client and team
Complete handover of all documentation and system | 23/10/2022 | client and team